## Summary of Test Execution
System Name:
Test Date:
Test Executed By:
Summary of Test Execution
Test Cycle: | 1
Overall Pass Rate: | 95.08%
Overall Fail Rate: | 4.918%

## Test Cases Executed
Test Case # | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail | Remarks
Musuem Attendance Monitoring System
Super Admin
TC-SA-01 | Super Admin Login | 1. Open login page 2. Click Super Admin 3. Enter valid email/username and password 4. Complete reCAPTCHA 5. Click Login | valid email | Successfully logged in and redirected to Super Admin Dashboard. |  | Pass
TC-SA-01.1 | Invalid Login Credentials | 1.Open Super Admin login modal 2. Enter wrong email or password 3. Complete reCAPTCHA 4. Click Login | valid credentials | Error message (e.g. Invalid credentials / Login Failed). |  | Pass
TC-SA-01.2 | Empty Email/Identifier Field | 1. Open Super Admin login 2. Leave identifier empty; enter password 3. Complete reCAPTCHA 4. Click Login | Identifier: (empty); Password: ******** | Validation error: Username or email is required. |  | Pass
TC-SA-01.3 | Empty Password Field | 1. Open Super Admin login 2. Enter valid identifier; leave password empty 3. Complete reCAPTCHA 4. Click Login | Identifier: test@example.com; Password: (empty) | Validation error: Password must be at least 6 characters. |  | Pass
TC-SA-01.4 | reCAPTCHA Not Completed | 1. Open Super Admin login 2. Enter valid credentials 3. Do NOT complete reCAPTCHA 4. Click Login | Valid Super Admin credentials | Error: Please complete the reCAPTCHA verification. |  | Pass
TC-SA-02 | Super Admin Login via Google | 1. Open Super Admin login 2. Click Sign in with Google 3. Select registered Google account | Google Email: (registered super admin) | Successfully authenticated and redirected to Super Admin Dashboard. |  | Pass
TC-SA-02.1 | Unauthorized Google Account | 1. Click Sign in with Google for Super Admin 2. Select unregistered Google account | Google Email: unregistered@example.com | Access denied; error (e.g. Super Admin account not found). |  | Pass
TC-SA-03 | Forgot Password – Request Code | 1. Open Super Admin login 2. Click Forgot Password 3. Enter registered email 4. Submit | valid email | Message: A 6-digit reset code has been sent. Check your inbox. |  | Pass
TC-SA-03.1 | Forgot Password – Invalid Email | 1. Open Forgot Password 2. Enter unregistered or invalid email 3. Submit | Email: invalid@example.com | Error (e.g. No super admin account found / valid email required). |  | Pass
TC-SA-03.2 | Reset Password with Code | 1. Request reset code 2. Enter 6-digit code from email 3. Enter new password (8+ chars; upper; lower; number) 4. Confirm 5. Submit | Code: (from email); ********; Confirm: ******** | Password reset successfully. You can now login. |  | Pass
TC-SA-04 | Super Admin Dashboard Access | 1. Login as Super Admin 2. View dashboard | Valid Super Admin credentials | Dashboard displays (e.g. login records; overview). |  | Pass
TC-SA-05 | Update Super Admin Profile | 1. Login as Super Admin 2. Click profile in sidebar 3. Update name; email; username; optionally upload image (max 5MB) 4. Save | Name; Email; Image: profile.jpg (≤5MB) | Profile updated successfully!; changes reflected in sidebar. |  | Pass
TC-SA-06 | Manage Admins – View List | 1. Go to Manage Admins | Valid Super Admin | List of admin accounts displayed. |  | Pass
TC-SA-07 | Manage Admins – Create Admin | 1. In Manage Admins click Add 2. Enter username; email; 3. Submit | valid credentials | Admin created; password auto-generated and sent to email. |  | Pass
TC-SA-08 | Manage Admins – Update Admin | 1. In Manage Admins select an admin 2. Edit username/email 3. Save | Updated credentials | Admin updated successfully. |  | Pass
TC-SA-09 | Manage Admins – Deactivate Admin | 1. In Manage Admins deactivate an admin 2. Confirm | Admin ID: (existing) | Admin deactivated; cannot login until reactivated. |  | Fail
TC-SA-10 | Manage Admins – Delete Admin | 1. In Manage Admins delete an admin 2. Confirm | Admin ID: (existing) | Admin permanently deleted. |  | Pass
TC-SA-11 | Module Permissions – View/Edit | 1. Go to Module Permissions 2. View or edit permissions per admin | Valid Super Admin | Permissions displayed and saved. |  | Pass
TC-SA-12 | Report Templates – View List | 1. Go to Report Templates | Valid Super Admin | List of report templates displayed. |  | Pass
TC-SA-13 | Report Templates – Create Template | 1. In Report Templates create new 2. Define name; fields; layout 3. Save | Template name and structure | Template created. |  | Pass
TC-SA-14 | Report Templates – Edit/Delete | 1. Edit or delete an existing report template 2. Save or confirm | Template ID: (existing) | Template updated or removed. |  | Pass
TC-SA-15 | Audit Logs – View | 1. Go to Audit Logs 2. View activity list | Valid Super Admin | Audit log entries displayed. |  | Pass
TC-SA-16 | Settings – View/Update Museum Settings | 1. Go to Settings 2. View or update museum settings 3. Save | Museum name; hours; contact | Settings saved. |  | Fail
TC-SA-17 | Logout | 1. Click Logout | Valid Super Admin | Logged out; redirected to login. |  | Pass
Admin
TC-AD-01 | Admin Login | 1. Open login page. 2. Click Administrator. 3. Enter valid email/username and password. 4. Complete reCAPTCHA. 5. Click Login. | valid credentials | Successfully logged in and redirected to Admin Dashboard. |  | Pass
TC-AD-01.1 | Invalid Admin Credentials | 1. Open Administrator login. 2. Enter wrong email or password. 3. Complete reCAPTCHA. 4. Click Login. | Email: test@example.com; Password: ******** | Error: Invalid credentials / Login Failed. |  | Pass
TC-AD-01.2 | Empty Identifier | 1. Open Administrator login. 2. Leave identifier empty. 3. Complete reCAPTCHA. 4. Click Login. | Identifier: (empty); Password: ******** | Username or email is required. |  | Pass
TC-AD-01.3 | Empty Password | 1. Open Administrator login. 2. Enter identifier; leave password empty. 3. Complete reCAPTCHA. 4. Click Login. | Identifier: test@example.com; Password: (empty) | Password must be at least 6 characters. |  | Pass
TC-AD-01.4 | reCAPTCHA Not Completed | 1. Enter valid Admin credentials. 2. Do not complete reCAPTCHA. 3. Click Login. | Valid Admin credentials | Please complete the reCAPTCHA verification. |  | Pass
TC-AD-02 | Admin Login via Google | 1. Open Administrator login. 2. Click Sign in with Google. 3. Select registered Admin Google account. | Google Email: (registered admin) | Authenticated and redirected to Admin Dashboard. |  | Pass
TC-AD-02.1 | Unauthorized Google Account (Admin) | 1. Click Sign in with Google for Administrator. 2. Select unregistered Google account. | Google Email: unregistered@example.com | Error: Admin account not found or Google auth failed. |  | Pass
TC-AD-03 | Forgot Password – Request Code | 1. Open Administrator login. 2. Forgot Password 3. Enter registered email 4. Submit. | valid credentials | A 6-digit reset code has been sent. Check your inbox. |  | Pass
TC-AD-03.1 | Forgot Password – Invalid Email | 1. Forgot Password. 2. Enter unregistered email. 3. Submit. | Email: invalid@example.com | No admin account found or valid email error. |  | Pass
TC-AD-03.2 | Reset Password with Code | 1. Request code. 2. Enter 6-digit code. 3. New password (8+ chars; upper; lower; number). 4. Confirm. 5. Submit. | Code: (from email); ********; Confirm: ******** | Password reset successfully. You can now login. |  | Pass
TC-AD-04 | Admin Dashboard Access | 1. Login as Admin. 2. View dashboard. | Valid Admin credentials | Dashboard displays (e.g. bookings; stats). |  | Pass
TC-AD-05 | Update Admin Profile | 1. Click profile in sidebar. 2. Update name; email; username; optional photo; optional new password. 3. Save. | Name; Email; Image (≤5MB); New password: ******** | Profile updated successfully! |  | Pass
TC-AD-05.1 | Profile – Password Mismatch | 1. In profile enter new password and different confirm password. 2. Save. | New: ********; Confirm: ******** | New password and confirm password do not match. |  | Pass
TC-AD-05.2 | Profile – Password Too Short | 1. In profile enter new password < 6 characters. 2. Save. | New: ********; Confirm: ******** | Password must be at least 6 characters long. |  | Pass
TC-AD-06 | Bookings – View List | 1. Go to Bookings. | Valid Admin (with booking access) | List of guest bookings (pending; confirmed; cancelled). |  | Pass
TC-AD-07 | Bookings – Confirm/Cancel Booking | 1. In Bookings select a pending booking. 2. Confirm or Cancel. | Booking ID: (existing) | Status updated; guest sees status in Booking Status. |  | Pass
TC-AD-08 | Attendance – View Records | 1. Go to Attendance (if permission enabled). | Admin with attendance module |  |  | Pass
TC-AD-09 | Attendance – Check-in / Check-out | 1. In Attendance perform check-in or check-out. | Admin user | Attendance logged; records update. |  | Pass
TC-AD-10 | Gallery – View/Manage Exhibits | 1. Go to Gallery. 2. View list; add/edit/delete if supported. | Admin with gallery module | Exhibits list; CRUD works. |  | Pass
TC-AD-11 | Reports – View/Generate | 1. Go to Reports. 2. Select template/date range. 3. Generate report. | Valid Admin; report template | Report generated (e.g. PDF). |  | Pass
TC-AD-11.1 | Reports - Automatic Report Generation | Click generate report Click export pdf,excel, &CSV | (none) | Automatic download reports without choosing template |  | Pass
TC-AD-12 | Settings – View/Update (Admin) | 1. Go to Settings. 2. View or update allowed settings. | Valid Admin | Settings viewed/saved within Admin scope. |  | Fail
TC-AD-13 | No Access to Manage Admins | 1. Login as Admin. 2. Check sidebar. | Valid Admin | Manage Admins and Report Templates NOT visible. |  | Pass
TC-AD-15 | Logout | 1. Login as Admin. 2. Click Logout. | Valid Admin | Logged out; redirected to login. |  | Pass
Guest
TC-GU-01 | Guest Home Page Access | 1. Open localhost:5173/guest | (none) | Home page loads (BSC-System); no login required. |  | Pass
TC-GU-02 | Guest – View Gallery/Exhibits | 1. On guest site go to Exhibits/Gallery section. | (none) | Gallery/exhibits displayed. |  | Pass
TC-GU-03 | Guest – Navigate to Book a Visit | 1. Click Book a Visit or go to /guest/book. | (none) | Booking page with form (name; email; date; time; etc.). |  | Pass
TC-GU-04 | Guest – Submit Valid Booking | 1. On Book a Visit fill all required fields 2. Select available date and time 3. Submit | Full name; valid email; valid PH contact (09xxxxxxxxx); date; time; purpose; visitors | Success message; booking created (e.g. pending). |  | Pass
TC-GU-04.1 | Guest – Booking Empty Required Field | 1. Leave one required field empty 2. Submit | Other fields valid | Validation error on empty required field. |  | Pass
TC-GU-04.2 | Guest – Booking Invalid Email | 1. Enter invalid email 2. Submit | Email: invalid-email | Validation error: valid email required. |  | Pass
TC-GU-04.3 | Guest – Booking Invalid Contact Number | 1. Enter invalid contact number 2. Submit | Contact: 123 or invalid | Validation error for valid Philippine mobile. |  | Pass
TC-GU-04.4 | Guest – Booking Unavailable Date/Time | 1. Select date/time not in available slots 2. Submit | Date: past or disabled; Time: disabled | Slot not selectable or error. |  | Pass
TC-GU-05 | Guest – View Booking Status | 1. Click Booking Status 2. Enter reference/email if required 3. View status | Booking reference or email | Modal/page shows status (Pending/Confirmed/Cancelled). |  | Pass
TC-GU-06 | Guest – About Us Page | 1. Go to /guest/about or About Us link. | (none) | About page loads (mission; vision; history). |  | Pass
TC-GU-07 | Guest – Contact / About Museum | 1. Scroll to contact section or contact page. | (none) | Museum contact info; mission/vision displayed. |  | Pass
TC-GU-08 | Guest – No Access to Admin Routes | 1. As guest open /admin or /login. | (none) | /admin redirects to login; guest cannot see admin dashboard. |  | Pass
TC-GU-09 | Guest – Announcements Visible | 1. View guest home or main page. | (none) | Announcements (if any) displayed. |  | Pass

## Defects Identified
Defect ID | Test Case ID | Description | Severity | Status | Assigned To | Date Reported | Date Fixed | Comments
D001 | TC004 | Deleted emails still visible in the Inbox | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | Deleted emails still visible in the Inbox | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | Deleted emails still visible in the Inbox | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | Deleted emails still visible in the Inbox | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | Deleted emails still visible in the Inbox | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | Deleted emails still visible in the Inbox | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | Deleted emails still visible in the Inbox | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.

## Exploratory Testing
Defect ID | Test Case ID | Description | Severity | Status | Assigned To | Date Reported | Date Fixed | Comments
D001 | TC004 | Add more alerts on every transactions | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | Properly labelled the form, put indicators for error handling | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | identify required fields. | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | proper use of data for testing | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | Enhance UI/Cosmetics | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | required password to delete accounts and capstone. | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
D001 | TC004 | admin account can't notified. | High | Open | [to be filled out by system's developers] | 2024-02-25 | [to be filled out by system's developers] | During the execution of TC004, the expected result was not met as deleted emails were still visible in the Inbox. This suggests a potential issue with the deletion process not updating the Inbox view correctly. Further investigation needed.
teachers can't view submitted capstones

## Severity Levels Guide
Severity Level | Description | When to Use | Guidelines | Example
Critical | Issues that completely block or "stop" the normal functioning of the system. The software is unusable or a significant part of it is not functioning. | Use this level when the defect prevents further testing or the software cannot be used at all. | Reserved for issues that halt all testing or prevent essential functions. | Users are unable to log in to the email system
High | Issues that have a significant impact on the functionality, causing major disruptions or impairing the core features. | Use for defects that have a serious impact on the system but do not completely block its use. | Used for severe issues that significantly impact the system but do not completely halt it. | Emails sent from the system are not reaching the recipients.
Medium | Issues that have a noticeable impact but don't critically affect core functionalities. They may affect non-essential features or have workarounds available. | Use for defects that are important but not critical to the overall system. | Applied to important issues that need attention but don't critically affect core functionalities. | Attachments in emails take longer than expected to upload.
Low | Issues that have a minor impact on the software. These defects are generally cosmetic or have little effect on system functionality. | Use for issues that are of low priority, such as minor visual imperfections or inconveniences. | For less critical issues that can be addressed after higher severity defects. | The spell-check feature is not working in the email composer.
Cosmetic | Minor issues that do not affect functionality and have little to no impact on the user experience. | Use for purely aesthetic issues or other trivial matters that do not impact the software's operation. | For issues that are minimal and have no significant impact on functionality. | The color of the "Compose" button is slightly different from the design specifications.